| Weekly Governance Progress Report |  |  |  |
| --- | --- | --- | --- |
| Team Name: | Team Portfolio Executive | Document Owner: | Week Ending Date: |
|  | George E. Crayton | Valecia Wahyon-Diggs |  |
| Status Meeting for: (Date) Attendees: |  |  |  |
|  |  | Document: N/A |  |
|  |  | Reporting compliance: Every Friday by CoB |  |
| Overall Progress Status: Definitions: _ ____ Blue items are tracking as [in-progress]. Status is currently underway and progressing normally Red item has is tracking as [no alternative], high-risk/impact to the project Yellow item is tracking as [] next-steps action or a start date. It presents a risk |  |  |  |

Task Overall Activity Summary for This Week

Status                             % Completed                            Notes

| Total Tech Status | On Track | 17 | 85% done, the remaining 15% is what we are looking which 17% is done |
| --- | --- | --- | --- |
| Total Operations Status |  | 30% | Operations: Staff training completed, sales field reps branded, and trade engagement commenced. |
| Total Sales & Marketing Status | On Track | 27 | Percentage calculation seems off. |
| Total Accounting & Finance Status |  |  |  |
| Tech: Final QA Testing - at 95% completed, last day is today Installation of Antivirus on the Production servers - bought antivirus and installation will start this week - Installation of Antivirus on Kola team devices - bought antivirus and installation will start this week Support Stakeholders meeting - -held meeting last week to get an idea of how support will work Network Monitoring and Customer Support Strategy - -started the documentation for Kola support - -researching a better ticketing tool to support both customer service and IT |  |  |  |
| Operations: |  |  |  |
| Sales and Marketing: Creatives, IDs, BB pricing, Promo items printed, Kiosk Pricing, QA/Focus Group Completed, SM plan finalized |  |  |  |

Activity Summary Activities Accomplished This Week

Status		                Notes

| Tech: On track with meeting the 25, November | ON TRACK | No major issues from QA testing. We will be wrapping up on the 25th and have the apps ready for the “Soft Go-live” on November 27, 2023 |
| --- | --- | --- |
| Sales and Marketing | ON TRACK |  |

Summary Activities Planned for Upcoming Week

Tech: Complete the following: - Installation of Antivirus on the Production servers - Installation of Antivirus on Kola team devices - Complete QA testing - Complete Support team training - Complete Apps on Apple Store

Operations:

Sales and Marketing:

Accounting and Finance:

Milestone and Deliverable Status

### Deliverable/Milestone1	     Target Date      Status	    Projected Date	       Notes

| Tech: QA Testing - 11/20/2023 Installation Antivirus on Production – 11/24/23 Support Training – 11/22/23 Apps Available on both Stores 11/25/2023 VM NSX Upgrade – 12/8/2023 | See next to event | On Track |  | The VM NSX Upgrade is in parallel with the rest of development. Kola will migrate to this Production system in 1st week of December 2023 |
| --- | --- | --- | --- | --- |
| Operations: |  |  |  |  |
| Sales and Marketing: |  |  |  |  |
| Accounting and Finance: |  |  |  | . |

Project Impact Issues Impeding Progress

### Brief Description                                       Impact                     Significance               Update

| Tech: The VM NSX Upgrade | This is in parallel and will require additional migration of the Production system | Rebuilding of the VPN | In Progress |
| --- | --- | --- | --- |
| Operations: |  |  |  |
| Sales and Marketing: |  |  |  |
| Accounting and Finance: |  |  |  |

Assigned Risks

### Brief Description		                 Significance	         Owner		Actions Taken

| Tech: |  |  |  |
| --- | --- | --- | --- |
| Operations: |  |  |  |
| Sales and Marketing: |  |  |  |
| Accounting and Finance: |  |  |  |

3 Impact can be:  Scope, Cost, Schedule, and Quality

4 Significance can be:  High, Medium, and And Low