| Weekly Progress Report |  |  |  |
| --- | --- | --- | --- |
| Team Name: | Team Portfolio Executive | Document Owner: | Week Ending Date: |
| IT Tech | George E. Crayton | Valecia Wahyon-Diggs | 11/24/2023 |
| Status Meeting for: (Date) Attendees: George Crayton Yves MBondji Valecia Diggs |  |  |  |
|  |  | Document: N/A |  |
|  |  | Reporting compliance: Every Friday by CoB |  |
| Overall Progress Status: Definitions: _ ____ Blue items are tracking as [in-progress]. Status is currently underway and progressing normally Red item has is tracking as [no alternative], high-risk/impact to the project Yellow item is tracking as [pending] next-steps action or a start date. It presents a risk |  |  |  |

Overall Activity Summary for This Week

Task

Status                             % Completed                            Notes

| Tech Total Progress: Overall, we are at 98%. We are working hard to meet our deadline. | In-Progress | 98% | Overall, we are at 98%. We are working hard to meet our deadline. We ran into an issue with the code Compiler that took time away from us working on the 3 major defects that needed to be resolved. |
| --- | --- | --- | --- |

Activity Activities Accomplished This Week

Status		                Notes

| Completed: QA Testing went well. No major showstopper. However, there were a few tickets that could've impacted Kola. Those defects were either resolved or being worked on by Dev. 1. CBL Exchange Rate modification on the platform 2. Buying MTN AirTime for others 3. Making a Merchant Payment Using QR Code 4. Public/Sponsor Voucher Applicants were not receiving SMS after registration | ON TRACK | We completed the following: - CBL Exchange Rate modification on the platform - Making a Merchant Payment Using QR Code - 4. Public/Sponsor Voucher Applicants were not receiving SMS after registration As mentioned, issue #2 is still in progress due to additional Compiler error that need immediate attention |
| --- | --- | --- |
| The www.kolafinancial.com site completed | ON TRACK | The www.kolafinancial.com website is up and running. We were able to retrieve the source code for both websites and the USSD. |
| Tech and Operations Legal Documentation for Go-live | ON TRACK | Reviewed and updated the Kola Legal and Financial Documents needed which were submitted to Mr. Crayton. Documents for Merchant, Agent, Partners, Change Request Form for Exchange Rate, Service Providers (Libango and Sochitel), and more. |
| Defects Status Report Total Defects: 14 Fixed and Tested: 5 Moving to Post Go-live: 4 Remaining: 5 | ON TRACK | Issues still outstanding that may not make it for Monday 1. Due to Apple's restrictions, the iOS part of Kola may not make Monday's Go-live, Dev is still working on it 2. Antivirus on the Production server will be delayed due to OVH setup A server agent to install the antivirus is needed. Yves is working through it 3. Buying MTN AirTime for others |
| Installation of Antivirus on the Production servers | In Progress | Waiting on purchasing of the antivirus |
| Installation of Antivirus on Kola team devices | In Progress | Waiting on purchasing of the antivirus |
| Apple Store Account Preparation for public access | In Progress |  |
| Azure DevOps project configuration (USSD and Website under source control, continuous integration) | In Progress | We found the Source Code for the following. Thanks to Yves and Edward. We started the AzureDevOps configuration for Visual Studio Code to be able to access the code for the following: USSD kolafinancial.com kolakash.com |
| Visual Studio Dev Env for Val | In Progress | We found the Source Code for the following. Thanks to Yves and Edward. We started the AzureDevOps configuration for Visual Studio Code to be able to access the code for the following: USSD kolafinancial.com kolakash.com |
| New Ticketing System Setup and Training for all Support teams | In Progress | Need to set up initial meeting with all stakeholders |

Activities Planned for Upcoming Week

### Activity					Status2                    	Notes

| Validate Google Play Store Apps Download | In Progress |  |
| --- | --- | --- |
| Network and Monitoring Strategy | In Progress |  |
| Network and Monitoring Employee Training | In Progress |  |
| Application and Development Employee Training | In Progress |  |
| Test Environment | In Progress | The testing environment server installation and configuration has started |
| Backup and Recovery | NOT STARTED |  |
| Deployment and Maintenance | NOT STARTED |  |

Milestone and Deliverable Status

### Deliverable/Milestone1	     Target Date      Status	    Projected Date	       Notes

| Kolafinancial website is up and running (www.kolakfinancial.com) |  | Completed |  | All SSL certificates were installed, and site is up and running |
| --- | --- | --- | --- | --- |
| Defects Status Report Total Defects: 14 Fixed and Tested: 5 Moved to Post Go-live: 4 Remaining: 5 | Nov, 27, 2023 | COMPLETED |  | Only 1 major defect remaining that could impact go-live. The dev team is working to get it completed asap. |
|  |  |  |  | . |

Project Impact Issues Impeding Progress

### Brief Description                                       Impact                     Significance               Update

Assigned Risks

### Brief Description		                 Significance	         Owner		Actions Taken

3 Impact can be:  Scope, Cost, Schedule, and Quality

4 Significance can be:  High, Medium, and And Low